1. literature review survey -

1. Selecting base papers and papers around that paradigms and preparing review & ppt for these papers

By 30th march

2.Looking into all datasets used and models proposed in these papers / sidewise writing survey report.

1st -10th April.

Tentative timelines

1. Run selected baseline models, understand code in the papers and perform comparison with SOA models.

10th April –25th April.

1. Identification of possible novel approach and implementation.

25th April –20th May

D. Writing report & presentation and final submission

30th may – 10th June

Break -20th May -30th May